## Change Register
Ref # | Date Identified | Source | Framework / Regulation | Change Description | Change Type | Initial Relevance | Analyst | Change Brief Prepared? | Triage Date | Control Mapping Impact | New Requirements Impact | Regulatory Impact | Evidence Impact | Overall Rating | Escalation Route | Decision | Decision Date | Policy Owner Assigned | Target Completion | Status | Closure Date | Closure Rationale / Notes
FCR-001 | 26/02/2024 | NIST CSRC Publication Alert | NIST CSF | NIST Cybersecurity Framework updated from v1.1 to v2.0. New Govern (GV) function introduced. Subcategories restructured. Informative references updated. Scope expanded beyond critical infrastructure. | Major version release | Relevant | J. Smith | Yes | 04/03/2024 | High | High | Medium | Medium | Significant | IS Governance Committee | Approved – full update programme | 11/03/2024 | A. Johnson | 10/06/2024 | Closed | 10/06/2024 | All policies updated to CSF 2.0. Govern function addressed in new Cybersecurity Governance Policy. Crosswalk completed. Assurance verification confirmed embedding.
FCR-002 | 15/05/2024 | PRA Regulatory Updates Email | PRA SS2/21 | PRA published updated supervisory statement SS2/21 with minor clarifications on mapping and reporting expectations for operational resilience. No new requirements introduced. | Minor update | Relevant | J. Smith | Yes | 20/05/2024 | Low | Low | Low | Low | Low | GRC team sign-off | Closed – no policy update required | 22/05/2024 |  |  | Closed | 22/05/2024 | Editorial clarifications only. No impact on current policy alignment. Logged for audit trail.
FCR-003 | 03/09/2024 | NIST CSRC Publication Alert | NIST CSF 2.0 | NIST published updated Quick Start Guides and Community Profile templates for CSF 2.0 implementation support. | Supplementary guidance | Not relevant | J. Smith | No | [11 empty] | Closed | 03/09/2024 | Implementation guidance only. No change to framework requirements. No triage required.

## Dashboard
Framework Change Register – Summary Dashboard
Total Changes Logged | 3
Open Items | 0
Closed Items | 3
By Overall Rating
Significant | 1
Medium | 0
Low | 1
By Status
Open | 0
In triage | 0
Escalated | 0
In progress | 0
Closed | 3

## Triage Criteria Reference
Triage Criteria Reference Guide
Criterion | Description | High | Medium | Low
Control mapping impact | Does the change affect controls currently mapped to our policy framework? | Structural changes to categories or subcategories | Renumbering or reorganisation only | Editorial or cosmetic changes
New requirements | Does the change introduce requirements not currently addressed? | New function or category introduced | New subcategories under existing functions | Expanded guidance only
Regulatory impact | Does the change affect how we evidence compliance with PRA, FCA, or other regulatory obligations? | Direct regulatory reference to the framework | Indirect (used to evidence compliance) | No regulatory linkage
Evidence and reporting | Does the change affect how we report, measure, or evidence compliance? | Assessment methodology changed | Informative references or mappings updated | No change to evidence approach
Escalation Matrix
Overall Rating | Action | Governance Route | Timeline
Low | Log and close. GRC analyst documents rationale. | GRC team sign-off | 5 working days
Medium | Targeted policy amendments. Policy owner drafts changes. | Policy owner approval with GRC review | 20 working days
Significant | Full policy update programme. Gap analysis, stakeholder consultation, board approval. | IS Governance Committee | 60–90 working days